## P2-ZOI midline Gantt chart
Feed the Future P2-ZOI midline |  | MONTH
indicator assessment tasks and timeline |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | Undertake planning activities (prepare workplan with Gantt chart and list of deliverables) | bar: MONTH 1
2 | Conduct inception visit or virtual consultation | bar: MONTH 1
3 | Develop plan for obtaining ethical review from federal wide-certified and in-country IRB | bar: MONTH 1
4 | Prepare the survey protocol | bar: MONTH 1 to MONTH 3
5 | Develop a scope of work for the local survey implementation partner and issue a request for proposals (if applicable) | bar: MONTH 1 to MONTH 2
6 | Prepare the sampling design document | bar: MONTH 2 to MONTH 4
7 | Coordinate with the national statistics office to select primary sampling units | bar: MONTH 2 to MONTH 3
8 | Select local survey implementation partner and submit the subcontracting package to the USAID Contracting Officer for approval (if applicable) | bar: MONTH 2 to MONTH 3
9 | Issue subcontract to local survey implementation partner | bar: MONTH 2 to MONTH 3
10 | Procure supplies and equipment (tablets and personal protective equipment) | bar: MONTH 2 to MONTH 4
11 | Customize the core main and parallel survey paper questionnaires as per country SOW | bar: MONTH 2 to MONTH 4
12 | Conduct initial capacity assessment of the in-country local survey implementation partner and develop a capacity strengthening plan | bar: MONTH 3 to MONTH 4
13 | Translate customized main and parallel survey paper questionnaires according to established translation protocol | bar: MONTH 3 to MONTH 4
14 | Submit application for review to the federal wide-certified IRB and in-country ethics committee | bar: MONTH 3 to MONTH 4
15 | Develop cognitive probes for the paper questionnaire pretest | bar: MONTH 4
16 | Implement paper questionnaire pretest according to established protocol | bar: MONTH 5
17 | Customize the core main and parallel survey CSPro CAPI data collection applications | bar: MONTH 4 to MONTH 6
18 | Prepare survey manuals: | bar: MONTH 4 to MONTH 6
a—Interviewer’s Manual | bar: MONTH 4 to MONTH 6
b—Field Supervisor’s Manual | bar: MONTH 4 to MONTH 6
c—Quality Control and Support Team Manual | bar: MONTH 4 to MONTH 6
d—In-Country Data Manager’s Manual | bar: MONTH 4 to MONTH 6
19 | Prepare fieldwork management plan, including the field movement plan, field check tables, data quality control plan | bar: MONTH 4 to MONTH 7
20 | Develop plans to train survey staff | bar: MONTH 4 to MONTH 7
21 | Develop training materials for all survey staff trainings: | bar: MONTH 4 to MONTH 7
a—Interviewers’ training | bar: MONTH 4 to MONTH 7
b—Field Supervisors’ training | bar: MONTH 4 to MONTH 7
c—QCS Teams’ training | bar: MONTH 4 to MONTH 7
d—ICDM’s training | bar: MONTH 4 to MONTH 7
22 | Implement household listing operation according to the CAPI Household Listing Manual | bar: MONTH 6 to MONTH 7
23 | Prepare listing data and select households (on a rolling basis) | bar: MONTH 6 to MONTH 7
24 | Ensure that IRB approvals have been received | bar: MONTH 7
25 | Implement training of trainers and CSPro CAPI pretest according to the CAPI pretest protocol | bar: MONTH 7 to MONTH 8
26 | Implement Interviewers’ training and pilot according to the pilot protocol | bar: MONTH 8
27 | Implement fieldwork | bar: MONTH 9 to MONTH 12
28 | Generate field check tables | bar: MONTH 9 to MONTH 13
29 | Prepare data weighting protocol | bar: MONTH 9 to MONTH 12
30 | Process data in CSPro according to Feed the Future’s standard data processing and finalization procedures | bar: MONTH 13 to MONTH 15
31 | Calculate sample weights and add to the data | bar: MONTH 13 to MONTH 14
32 | Prepare the data quality assessment memo | bar: MONTH 15
33 | Analyze the data and prepare midline indicator assessment results tables | bar: MONTH 15 to MONTH 20
34 | Draft midline indicator assessment report, including three rounds of review and revision | bar: MONTH 17 to MONTH 20
35 | Prepare and conduct survey results dissemination presentation | bar: MONTH 17 to MONTH 21
36 | Develop communication products as per the agreed scope of work | bar: MONTH 17 to MONTH 23
37 | Prepare non-public, restricted, public access datasets, including supporting materials | bar: MONTH 17 to MONTH 20
38 | Enter values in USAID’s Development Information Solution | bar: MONTH 20
39 | Upload final midline indicator assessment report to the Development Experience Clearinghouse after USAID receives approval by the host country government | bar: MONTH 20 to MONTH 23
40 | Conduct final capacity strengthening assessment and write final capacity strengthening report (if applicable) | bar: MONTH 21 to MONTH 23
41 | Upload final, COR-approved communications products to the Development Experience Clearinghouse | bar: MONTH 21 to MONTH 23
Capacity Strengthening
CS1 | Placeholder for local survey implementation partner capacity strengthening activities X] | bar: MONTH 7 to MONTH 23
CS2 | Placeholder for capacity strengthening activities [X] for other stakeholders (as applicable) | bar: MONTH 5 to MONTH 23