## About the Survey Tracker
FEED THE FUTURE SURVEY IMPLEMENTATION DOCUMENT
Survey Implementation Tracker Zone of Influence Midline Survey [COUNTRY] [YEAR]
ABOUT THE FEED THE FUTURE ZONE OF INFLUENCE MIDLINE SURVEY IMPLEMENTATION TRACKER:
The Feed the Future Survey Implementation Tracker consists of a list of tasks and deliverables designed to help USAID Activity Managers systematically monitor and manage the implementation of surveys conducted for Feed the Future. Although this Tracker was designed to support the implementation of Feed the Future Zone of Influence population-based surveys, it can also be used to guide the implementation of other population-based surveys in developing country contexts (though timelines will need to be adjusted outward if not working with a pre-established set of core survey documents). When each of the steps and deliverables are executed by appropriately trained and experienced staff who are focused on ensuring quality and completeness, it is expected that this approach will produce a survey operation and survey data that are of a minimum defensible quality. This tracker serves as: - a map of the critical aspects of the survey processes that need to be in place to achieve minimum survey methodological standards; - a planning guide to support alignment of survey processes, staff, and resources; - a framework into which other Feed the Future Zone of Influence Midline Survey guidance documents fit, including the survey protocol; questionnaire; and training, interviewer, supervisor, and data management manuals; - a monitoring tool that helps managers to track overall survey progress, technical quality, deliverables, and other management aspects of the survey, and ensure none is skipped or forgotten.
HOW TO USE THE SURVEY TRACKER
Item | Description
Tasks: | All requisite tasks for the survey to be performed by the contractor are pre-filled in the tracker. Managers may adapt the tool by adding other specific tasks that they deem important.
Deliverable: | All key deliverables from each task are pre-filled in the tracker. Managers may wish to add more, depending on the extent to which very close management of the contractor may be required.
Status: | There are four status categories - Not Started, In Progress, Delayed, and Complete. For each task, indicate where it is in the process.
Dates: | All due dates for each deliverable should be discussed and agreed on before they are entered into the Tracker. Timelines vary for each deliverable, and the Survey Manager should use the Gantt Chart as a guide for estimating the dates. One to two weeks should be allowed to review deliverable submissions. Editing and formatting should also allow for two weeks.

## Survey Tracker Management Tool
Key: Survey Status Categories
|  |  | Not Started | In Progress | Delayed | Complete | Pending Approval | Approved
|  |  | OFF | OFF | OFF | OFF | OFF | OFF
|  |  |  | CONTRACTOR SUBMISSION |  | USAID REVIEW |  | CONTRACTOR REVISION, EDITING, AND FORMATTING |  | SUBMITTED | APPROVED
Feed the Future Zone of Influence Midline Survey Implementation Tracker
| TASK | DELIVERABLES | STATUS | START DATE | END DATE | START DATE2 | END DATE2 | DATE COMPLETED | DATE APPROVED | DATE SUBMITTED | DATE APPROVED2 | NOTES
1 | Undertake planning activities | Customized scope of work | Not Started
2 | Conduct inception visit | Inception visit report | Not Started
3 | Develop plan for obtaining ethical review from federalwide-certified and in-country IRB | Plan for obtaining ethical review from federalwide-certified and in-country IRB | Not Started
4 | Prepare the study protocol and accompanying implementation plan | Survey protocol | Not Started
5 | Develop and issue RFP (if required) | Scope of work (with detailed fieldwork implementation plan, including team structure, fieldwork timeline, and logistics), RFP | Complete
6 | Prepare the sampling design | Sampling design plan | Not Started
7 | Coordinate with national statistical office to select PSUs | List of selected clusters (first stage sampling) | Not Started
8 | Undertake country-specific customization of the core questionnaire (paper version) | Customized questionnaire (paper version) | Not Started
9 | Translate questionnaire (paper version) | Translated questionnaire (paper version) | Not Started
10 | Submit application for review to the IRB | Package of all IRB submission requirements for both international and in-country (if required) | Not Started
11 | Establish range values for purposes of implementing range checks | File of range values (indicating which questionnaire items will have range checks and what the ranges will be) | Not Started
12 | Subcontract to local partner organization | Contract signed with local survey organization | Not Started
13 | Customize core questionnaire pretest protocol (including cognitive probes) | Questionnaire pretest protocol (including cognitive probes) | Not Started
14 | Implement questionnaire pretest | Questionnaire pretest report | Not Started
15 | Procure supplies and equipment (tablets and personal protective equipment) | Supply ordering plan and timeline (including customs management plan if supplies are being shipped to country) | Not Started
16 | Develop CSPro CAPI pretest and pilot protocols | CSPro CAPI pretest and pilot protocols | Not Started
17 | Develop and code programming specifications for CSPro CAPI | Programming specification tables | Not Started
18 | Program questionnaire for CSPro CAPI data collection | CSPro CAPI data collection program | Not Started
19 | Prepare survey manuals: |  | Not Started
| 19a - Interviewer Manual | Customized Interviewer Manual | Not Started
| 19b - Supervisor Manual | Customized Supervisor Manual | Not Started
| 19c - Organization Manual | Customized Survey Organization Manual | Not Started
| 19d - Quality Control and Support Team Manual | Customized Quality Control and Support Team Manual | Not Started
| 19e - Listing Manual | Customized Listing Manual | Not Started
20 | Develop field check tables | Field check table shells | Not Started
21 | Develop data monitoring plan | Data monitoring plan | Not Started
22 | Prepare data cleaning plan | Data cleaning plan | Not Started
23 | Develop fieldwork management and monitoring plan | Detailed fieldwork management and monitoring plan that includes regular progress reports throughout fieldwork | Not Started
24 | Develop interviewer training plans and supporting materials |  | Not Started
| 24a - Training plan | Interviewer training plan | Not Started
| 24b - Agenda (facilitator and trainee versions) | Training agenda (facilitator and trainee versions) | Not Started
| 24c - Attendance sheets | Customized attendance sheets | Not Started
| 24d - Quizzes | Quizzes | Not Started
| 24e - Role play exercises | Role play exercises | Not Started
| 24f - Demonstration of field check tables and interpretation | Demonstration of field check tables and interpretation | Not Started
| 24g - Demonstration of real-time remote fieldwork monitoring (if planned) | Demonstration of real-time remote fieldwork monitoring | Not Started
| 24h - CSPro CAPI training materials | CSPro CAPI training materials | Not Started
| 24i - Interviewer's training materials (slides, specific forms) | Interviewer training materials (including customized slides and forms) | Not Started
| 24j - Supervisor training materials (incl. assignment and control sheets) | Supervisor training materials (including assignment and control sheets) | Not Started
| 24k - IT staff training plan and materials (if relevant) | IT staff training plan and materials | Not Started
25 | Implement listing operation | Listing field report and household listing | Not Started | [9 empty] | .
26 | Clean listing data and select households (on a rolling basis) | List of households selected for interview | Not Started
27 | Ensure that IRB approval has been received | Approval from Federalwide-certified IRB and local IRB | Not Started
28 | Implement training of trainers | Completion of training of trainers | Not Started
29 | Implement CSPro CAPI pretest (as part of training of trainers) | Training of trainers and CSPro CAPI pretest report | Not Started
30 | Implement interviewer training | Completion of interviewer training | Not Started
31 | Implement pilot (as part of interviewer training) | Interviewer training and pilot report | Not Started
32 | Implement data entry/data management pilot (as part of all-systems fieldwork pilot) | Data entry/data management pilot report | Not Started
33 | Prepare data weighting protocol | Data weighting protocol | Not Started
34 | Implement fieldwork | Weekly fieldwork report, plus summary fieldwork report at end of data collection activities | Not Started
35 | Generate field check tables | Weekly field check tables | Not Started
36 | Prepare data structure and codebook | Structure of the data files and expected format of the codebook | Not Started
37 | Clean the data | Memo advising of data cleaning steps implemented according to plan, and notable findings during the cleaning process | Not Started
38 | Weight the data | Memo advising that the weighting of the data has been completed according to protocol | Not Started
39 | Prepare data quality assessment memo | Memo to include response rates, final set of field check tables and interpretation of key findings, and any other pertinent information regarding data quality | Not Started
40 | Analyze the data | Produce frequencies, cross-tabulations, and any additional required statistical analyses | Not Started
41 | Prepare final report tables | Final report tables (draft, final) | Not Started
42 | Draft final report | Final report text (draft, final) | Not Started
43 | Prepare protocol for rendering data suitable for public use | Protocol for preparation of public access data | Not Started
44 | Prepare non-public access data files (maintains some PII, e.g., GPS coordinates) | Non-public access data files and supporting materials | Not Started
45 | Prepare restricted access data files | Restricted access data files and supporting materials | Not Started
46 | Prepare public access data files (excludes PII) | Public access data files and supporting materials | Not Started
47 | Enter values in USAID'S Development Information Solution | Indicator estimates entered in USAID's Development Information Solution | Not Started

## Gantt Chart
Feed the Future Zone of Influence Midline Survey Tasks and Timeline |  | MONTH
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Undertake planning activities | bar: MONTH 1
2 | Conduct inception visit | bar: MONTH 1
3 | Develop plan for obtaining ethical review from federalwide-certified and in-country IRB | bar: MONTH 1
4 | Prepare the study protocol and accompanying implementation plan | bar: MONTH 1 to MONTH 3
5 | Develop and issue RFP (if required) | bar: MONTH 2
6 | Prepare the sampling design | bar: MONTH 2
7 | Coordinate with national statistical office to select PSUs | bar: MONTH 2 to MONTH 3
8 | Undertake country-specific customization of the core questionnaire (paper version) | bar: MONTH 2 to MONTH 3
9 | Translate questionnaire (paper version) | bar: MONTH 3
10 | Submit application for review to the IRB | bar: MONTH 3 to MONTH 4
11 | Establish range values for purposes of implementing range checks | bar: MONTH 3 to MONTH 4
12 | Subcontract to local partner organization | bar: MONTH 4
13 | Customize core questionnaire pretest protocol (including cognitive probes) | bar: MONTH 4
14 | Implement questionnaire pretest | bar: MONTH 5
15 | Procure supplies and equipment (tablets and personal protective equipment) | bar: MONTH 4 to MONTH 5
16 | Develop CSPro CAPI pretest and pilot protocols | bar: MONTH 4 to MONTH 5
17 | Develop and code programming specifications for CSPro CAPI | bar: MONTH 4 to MONTH 7
18 | Program questionnaire for CSPro CAPI data collection | bar: MONTH 4 to MONTH 6
19 | Prepare survey manuals: | bar: MONTH 4 to MONTH 6
19a - Interviewer Manual | bar: MONTH 4 to MONTH 6
19b - Supervisor Manual | bar: MONTH 4 to MONTH 6
19c - Organization Manual | bar: MONTH 4 to MONTH 6
19d - Quality Control and Support Team Manual | bar: MONTH 4 to MONTH 6
19e - Listing Manual | bar: MONTH 4 to MONTH 6
20 | Develop field check tables | bar: MONTH 4 to MONTH 7
21 | Develop data monitoring plan | bar: MONTH 4 to MONTH 7
22 | Prepare data cleaning plan | bar: MONTH 4 to MONTH 7
Feed the Future Zone of Influence Midline Survey Tasks and Timeline |  | MONTH 1: MONTH
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
23 | Develop fieldwork management and monitoring plan | bar: MONTH 4 to MONTH 7
24 | Develop interviewer training plans and supporting materials | bar: MONTH 4 to MONTH 7
24a - Training plan | bar: MONTH 4 to MONTH 7
24b - Agenda (facilitator and trainee versions) | bar: MONTH 4 to MONTH 7
24c - Attendance sheets | bar: MONTH 4 to MONTH 7
24d - Quizzes | bar: MONTH 4 to MONTH 7
24e - Role play exercises | bar: MONTH 4 to MONTH 7
24f - Demonstration of field check tables and interpretation | bar: MONTH 4 to MONTH 7
24g - Demonstration of real-time remote fieldwork monitoring (if planned) | bar: MONTH 4 to MONTH 7
24h - CSPro CAPI training materials | bar: MONTH 4 to MONTH 7
24i - Interviewer's training materials (slides, specific forms) | bar: MONTH 4 to MONTH 7
24j - Supervisor training materials (incl. assignment and control sheets) | bar: MONTH 4 to MONTH 7
24k - IT staff training plan and materials (if relevant) | bar: MONTH 4 to MONTH 7
25 | Implement listing operation | bar: MONTH 6 to MONTH 7
26 | Clean listing data and select households (on a rolling basis) | bar: MONTH 6 to MONTH 7
27 | Ensure that IRB approval has been received | bar: MONTH 7
28 | Implement training of trainers | bar: MONTH 7 to MONTH 8
29 | Implement CSPro CAPI pretest (as part of training of trainers) | bar: MONTH 7 to MONTH 8
30 | Implement interviewer training | bar: MONTH 8
31 | Implement pilot (as part of interviewer training) | bar: MONTH 8
32 | Implement data entry/data management pilot (as part of all-systems fieldwork pilot) | bar: MONTH 8
33 | Prepare data weighting protocol | bar: MONTH 8
34 | Implement fieldwork | bar: MONTH 9 to MONTH 13
35 | Generate field check tables | bar: MONTH 9 to MONTH 14
36 | Prepare data structure and codebook | bar: MONTH 14 to MONTH 17
37 | Clean the data | bar: MONTH 14 to MONTH 15
38 | Weight the data | bar: MONTH 14
39 | Prepare data quality assessment memo | bar: MONTH 16
40 | Analyze the data | bar: MONTH 16 to MONTH 19
41 | Prepare final report tables | bar: MONTH 18 to MONTH 19
42 | Draft final report | bar: MONTH 17 to MONTH 19
43 | Prepare protocol for rendering data suitable for public use | bar: MONTH 17 to MONTH 18
44 | Prepare non-public access data files (maintains some PII, e.g., GPS coordinates) | bar: MONTH 17 to MONTH 20
45 | Prepare restricted access data files | bar: MONTH 17 to MONTH 20
46 | Prepare public access data files (excludes PII) | bar: MONTH 18 to MONTH 20
47 | Enter values in USAID'S Development Information Solution | bar: MONTH 20
Notes: IRB – institutional review board; RFP – request for proposal; PSU – primary sampling unit; CAPI – computer-assisted personal interviewing; CSPro – census and survey processing system; PII – personally identifiable information
This Gantt chart is predicated on the use of existing core survey documentation (questionnaire, manuals, data entry program, etc.) that need only be customized for country-specific details. Addition of new questions, modules, or procedures will require considered revision and extension of the timeline represented here.