## Gantt Chart
Feed the Future Zone of Influence Midline Survey Core Gantt Chart
Feed the Future Zone of Influence Midline Survey Tasks and Timeline |  | MONTH
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Undertake planning activities | bar: MONTH 1
2 | Conduct inception visit | bar: MONTH 1
3 | Develop plan for obtaining ethical review from federalwide-certified and in-country IRB | bar: MONTH 1
4 | Prepare the study protocol and accompanying implementation plan | bar: MONTH 1 to MONTH 3
5 | Develop and issue RFP (if required) | bar: MONTH 2
6 | Prepare the sampling design | bar: MONTH 2
7 | Coordinate with national statistical office to select PSUs | bar: MONTH 2 to MONTH 3
8 | Undertake country-specific customization of the core questionnaire (paper version) | bar: MONTH 2 to MONTH 3
9 | Translate questionnaire (paper version) | bar: MONTH 3
10 | Submit application for review to the IRB | bar: MONTH 3 to MONTH 4
11 | Establish range values for purposes of implementing range checks | bar: MONTH 3 to MONTH 4
12 | Subcontract to local partner organization | bar: MONTH 4
13 | Customize core questionnaire pretest protocol (including cognitive probes) | bar: MONTH 4
14 | Implement questionnaire pretest | bar: MONTH 5
15 | Procure supplies and equipment (tablets and personal protective equipment) | bar: MONTH 4 to MONTH 5
16 | Develop CSPro CAPI pretest and pilot protocols | bar: MONTH 4 to MONTH 5
17 | Develop and code programming specifications for CSPro CAPI | bar: MONTH 4 to MONTH 7
18 | Program questionnaire for CSPro CAPI data collection | bar: MONTH 4 to MONTH 6
19 | Prepare survey manuals: | bar: MONTH 4 to MONTH 6
19a - Interviewer Manual | bar: MONTH 4 to MONTH 6
19b - Supervisor Manual | bar: MONTH 4 to MONTH 6
19c - Organization Manual | bar: MONTH 4 to MONTH 6
19d - Quality Control and Support Team Manual | bar: MONTH 4 to MONTH 6
19e - Listing Manual | bar: MONTH 4 to MONTH 6
20 | Develop field check tables | bar: MONTH 4 to MONTH 7
21 | Develop data monitoring plan | bar: MONTH 4 to MONTH 7
22 | Prepare data cleaning plan | bar: MONTH 4 to MONTH 7
Feed the Future Zone of Influence Midline Survey Tasks and Timeline |  | MONTH 1: MONTH
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
23 | Develop fieldwork management and monitoring plan | bar: MONTH 4 to MONTH 7
24 | Develop interviewer training plans and supporting materials | bar: MONTH 4 to MONTH 7
24a - Training plan | bar: MONTH 4 to MONTH 7
24b - Agenda (facilitator and trainee versions) | bar: MONTH 4 to MONTH 7
24c - Attendance sheets | bar: MONTH 4 to MONTH 7
24d - Quizzes | bar: MONTH 4 to MONTH 7
24e - Role play exercises | bar: MONTH 4 to MONTH 7
24f - Demonstration of field check tables and interpretation | bar: MONTH 4 to MONTH 7
24g - Demonstration of real-time remote fieldwork monitoring (if planned) | bar: MONTH 4 to MONTH 7
24h - CSPro CAPI training materials | bar: MONTH 4 to MONTH 7
24i - Interviewer's training materials (slides, specific forms) | bar: MONTH 4 to MONTH 7
24j - Supervisor training materials (incl. assignment and control sheets) | bar: MONTH 4 to MONTH 7
24k - IT staff training plan and materials (if relevant) | bar: MONTH 4 to MONTH 7
25 | Implement listing operation | bar: MONTH 6 to MONTH 7
26 | Clean listing data and select households (on a rolling basis) | bar: MONTH 6 to MONTH 7
27 | Ensure that IRB approval has been received | bar: MONTH 7
28 | Implement training of trainers | bar: MONTH 7 to MONTH 8
29 | Implement CSPro CAPI pretest (as part of training of trainers) | bar: MONTH 7 to MONTH 8
30 | Implement interviewer training | bar: MONTH 8
31 | Implement pilot (as part of interviewer training) | bar: MONTH 8
32 | Implement data entry/data management pilot as part of all-systems fieldwork pilot | bar: MONTH 8
33 | Prepare data weighting protocol | bar: MONTH 8
34 | Implement fieldwork | bar: MONTH 9 to MONTH 13
35 | Generate field check tables | bar: MONTH 9 to MONTH 14
36 | Prepare data structure and codebook | bar: MONTH 14 to MONTH 17
37 | Clean the data | bar: MONTH 14 to MONTH 15
38 | Weight the data | bar: MONTH 14
39 | Prepare data quality assessment memo | bar: MONTH 16
40 | Analyze the data | bar: MONTH 16 to MONTH 19
41 | Prepare final report tables | bar: MONTH 18 to MONTH 19
42 | Draft final report | bar: MONTH 17 to MONTH 19
43 | Prepare protocol for rendering data suitable for public use | bar: MONTH 17 to MONTH 18
44 | Prepare non-public access data files (maintains some PII, e.g., GPS coordinates) | bar: MONTH 17 to MONTH 20
45 | Prepare restricted access data files | bar: MONTH 17 to MONTH 20
46 | Prepare public access data files (excludes PII) | bar: MONTH 18 to MONTH 20
47 | Enter values in USAID'S Development Information Solution | bar: MONTH 20
Notes: IRB – institutional review board; RFP – request for proposal; PSU – primary sampling unit; CAPI – computer-assisted personal interviewing; CSPro – census and survey processing system; PII – personally identifiable information
This Gantt chart is predicated on the use of existing core survey documentation (questionnaire, manuals, data entry program, etc.) that need only be customized for country-specific details. Addition of new questions, modules, or procedures will require considered revision and extension of the timeline represented here.