## Gantt Chart
Feed the Future Zone of Influence Midline Survey Core Gantt Chart
Feed the Future Zone of Influence Midline Survey Tasks and Timeline |  | MONTH
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Undertake planning activities | bar: MONTH 1
2 | Conduct inception visit | bar: MONTH 1
3 | Develop plan for obtaining ethical review from federalwide-certified and in-country IRB | bar: MONTH 1
4 | Prepare the study protocol and accompanying implementation plan | bar: MONTH 1 to MONTH 3
5 | Develop and issue RFP (if required) | bar: MONTH 2
6 | Prepare the sampling design | bar: MONTH 2
7 | Coordinate with national statistical office to select PSUs | bar: MONTH 2 to MONTH 3
8 | Prepare the analysis plan | bar: MONTH 2 to MONTH 3
8 | Undertake country-specific customization of the core questionnaire (paper version) | bar: MONTH 2 to MONTH 3
9 | Translate questionnaire (paper version) | bar: MONTH 3
10 | Submit application for review to the IRB | bar: MONTH 3 to MONTH 4
11 | Establish range values for purposes of implementing range checks | bar: MONTH 3 to MONTH 4
12 | Subcontract to local partner organization | bar: MONTH 4
13 | Customize core questionnaire pretest protocol (including cognitive probes) | bar: MONTH 4
14 | Implement questionnaire pretest | bar: MONTH 5
15 | Procure supplies and equipment (tablets and personal protective equipment) | bar: MONTH 4 to MONTH 5
16 | Develop CSPro CAPI pretest and pilot protocols | bar: MONTH 4 to MONTH 5
17 | Develop and code programming specifications (tablets only) | bar: MONTH 4 to MONTH 7
18 | Program questionnaire for CSPro CAPI data collection or for PAPI data entry) | bar: MONTH 4 to MONTH 6
19 | Prepare survey manuals: | bar: MONTH 4 to MONTH 6
19a - Interviewer Manual | bar: MONTH 4 to MONTH 6
19b - Supervisor Manual | bar: MONTH 4 to MONTH 6
19c - Organization Manual | bar: MONTH 4 to MONTH 6
19d - Quality Control and Support Team Manual | bar: MONTH 4 to MONTH 6
19e - Listing Manual | bar: MONTH 4 to MONTH 6
20 | Develop field check tables | bar: MONTH 4 to MONTH 7
21 | Develop data monitoring plan | bar: MONTH 4 to MONTH 7
22 | Prepare data cleaning plan | bar: MONTH 4 to MONTH 7
Feed the Future Zone of Influence Midline Survey Tasks and Timeline |  | MONTH 1: MONTH
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
23 | Develop fieldwork management and monitoring plan | bar: MONTH 4 to MONTH 7
24 | Develop interviewer training plans and supporting materials | bar: MONTH 4 to MONTH 7
24a - Training plan | bar: MONTH 4 to MONTH 7
24b - Agenda (facilitator and trainee versions) | bar: MONTH 4 to MONTH 7
24c - Attendance sheets | bar: MONTH 4 to MONTH 7
24d - Quizzes | bar: MONTH 4 to MONTH 7
24e - Role play exercises | bar: MONTH 4 to MONTH 7
24f - Demonstration of field check tables and interpretation | bar: MONTH 4 to MONTH 7
24g - Demonstration of real-time remote fieldwork monitoring (if planned) | bar: MONTH 4 to MONTH 7
24h - CSPro CAPI training materials (if relevant) | bar: MONTH 4 to MONTH 7
24i - Interviewer's training materials (slides, specific forms) | bar: MONTH 4 to MONTH 7
24i - Supervisor training materials (incl. assignment and control sheets) | bar: MONTH 4 to MONTH 7
24j - IT staff training plan and materials (if relevant) | bar: MONTH 4 to MONTH 7
25 | Implement listing operation | bar: MONTH 6 to MONTH 7
26 | Clean listing data and select households (on a rolling basis) | bar: MONTH 6 to MONTH 7
27 | Ensure that IRB approval has been received | bar: MONTH 7
28 | Implement training of trainers | bar: MONTH 7 to MONTH 8
29 | Implement CSPro CAPI pretest (as part of training of trainers) | bar: MONTH 7 to MONTH 8
30 | Implement interviewer training | bar: MONTH 8
31 | Implement pilot (as part of interviewer training) | bar: MONTH 8
32 | Implement data entry/data management pilot as part of all-systems fieldwork pilot | bar: MONTH 8
33 | Prepare data weighting protocol | bar: MONTH 8
34 | Implement fieldwork | bar: MONTH 9 to MONTH 13
35 | Generate field check tables | bar: MONTH 9 to MONTH 14
36 | Prepare data structure and codebook | bar: MONTH 14 to MONTH 17
37 | Clean the data | bar: MONTH 14 to MONTH 15
38 | Weight the data | bar: MONTH 14
39 | Prepare data quality assessment memo | bar: MONTH 16
40 | Analyze the data | bar: MONTH 16 to MONTH 19
41 | Prepare final report tables | bar: MONTH 18 to MONTH 19
42 | Draft final report | bar: MONTH 17 to MONTH 19
43 | Prepare protocol for rendering data suitable for public use | bar: MONTH 17 to MONTH 18
44 | Prepare non-public access data files (maintains some PII, e.g., GPS coordinates) | bar: MONTH 17 to MONTH 20
45 | Prepare restricted access data files | bar: MONTH 17 to MONTH 20
46 | Prepare public access data files (excludes PII) | bar: MONTH 18 to MONTH 20
47 | Enter values in USAID'S Development Information Solution | bar: MONTH 20
Notes: IRB – institutional review board; RFP – request for proposal; PSU – primary sampling unit; CAPI – computer-assisted personal interviewing; CSPro – census and survey processing system; PII – personally identifiable information
This Gantt chart is predicated on the use of existing core survey documentation (questionnaire, manuals, data entry program, etc.) that need only be customized for country-specific details. Addition of new questions, modules, or procedures will require considered revision and extension of the timeline represented here.
Note on W11: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This is referred to as the DTAP in the Org Manual. We will align the terms. However, would like to confirm to delete the row since the Guide to Stat contains all the guidance. Reply: OK to delete the row
Note on W19: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: and personal protective equipment Reply: thank you
Note on W21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Move this before 18? Need programming specs to program. Reply: OK - thank you
Note on W30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Move before 20 as field check tables are a component of the data monitoring plan. Reply: OK - thanks
Note on W44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: What about interviewer training materials, e.g., ppts, etc. Reply: Replaced 'Agriculture-specific training materials' with 'Interviewer's training materials (slides, specific forms)'
Note on W54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Remove this line? - it's really incorporated in pilot....and also the CAPI pretest Reply: I understand why you're suggesting this; however, because I share this Gantt chart widely with non-survey experts, I do think it's good to keep it called out here specifically so they are explicitly aware of this step (which is implicitly understood by ICF). Reply: OK.
Note on W58: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should data structure be determined before 18 and 22? Also, move codebook down to after fieldwork?...because questionnaire is finalized up until fieldwork starts + analytic variables are added after analysis is complete. Reply: That sounds fine - thanks Reply: thanks Reply: Moved from months 4-7 to 14-17
Note on W60: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Data is partially cleaned before giving to Sampling Statistician to weight. Suggest we move down after 40? Reply: OK Reply: Done
Note on W65: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: This should come after the analysis is complete and the report is finalized so that you can thoroughly go through all variables? Move after 44? Reply: Sounds good - thanks Reply: Done
Note on W67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added row for restricted access data files
Note on W68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed "use" to "access" to alogn with data prep protocol. Add a row for restricted access data files? Reply: Yes please