## About the Survey Tracker
FEED THE FUTURE SURVEY IMPLEMENTATION DOCUMENT
Survey Implementation Tracker Zone of Influence Midline Survey [COUNTRY] [YEAR]
ABOUT THE FEED THE FUTURE ZONE OF INFLUENCE MIDLINE SURVEY IMPLEMENTATION TRACKER:
The Feed the Future Survey Implementation Tracker consists of a list of tasks and deliverables designed to help USAID Activity Managers systematically monitor and manage the implementation of surveys conducted for Feed the Future. Although this Tracker was designed to support the implementation of Feed the Future Zone of Influence population-based surveys, it can also be used to guide the implementation of other population-based surveys in developing country contexts (though timelines will need to be adjusted outward if not working with a pre-established set of core survey documents). When each of the steps and deliverables are executed by appropriately trained and experienced staff who are focused on ensuring quality and completeness, it is expected that this approach will produce a survey operation and survey data that are of a minimum defensible quality. This tracker serves as: - a map of the critical aspects of the survey processes that need to be in place to achieve minimum survey methodological standards; - a planning guide to support alignment of survey processes, staff, and resources; - a framework into which other Feed the Future Zone of Influence Midline Survey guidance documents fit, including the survey protocol; questionnaire; and training, interviewer, supervisor, and data management manuals; - a monitoring tool that helps managers to track overall survey progress, technical quality, deliverables, and other management aspects of the survey, and ensure none is skipped or forgotten.
HOW TO USE THE SURVEY TRACKER
Item | Description
Tasks: | All requisite tasks for the survey to be performed by the contractor are pre-filled in the tracker. Managers may adapt the tool by adding other specific tasks that they deem important.
Deliverable: | All key deliverables from each task are pre-filled in the tracker. Managers may wish to add more, depending on the extent to which very close management of the contractor may be required.
Status: | There are four status categories - Not Started, In Progress, Delayed, and Complete. For each task, indicate where it is in the process.
Dates: | All due dates for each deliverable should be discussed and agreed on before they are entered into the Tracker. Timelines vary for each deliverable, and the Survey Manager should use the Gantt Chart as a guide for estimating the dates. One to two weeks should be allowed to review deliverable submissions. Editing and formatting should also allow for two weeks.
Note on B3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added Midline
Note on B4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added ZOI Midline
Note on B5: Author: Added ZOI Midline

## Survey Tracker Mgmt Tool
Key: Status Categories
|  |  |  | Not Started | In Progress | Delayed | Complete
|  |  |  | OFF | OFF | OFF | OFF
Feed the Future Zone of Influence Midline Survey Implementation Tracker |  |  |  | Contractor Submission |  | USAID Review |  | Contractor Revision, Editing, and Formatting |  | Submitted | Approved
| Tasks | Deliverables | STATUS | START DATE | END DATE | START DATE2 | END DATE2 | START DATE | END DATE | DATE SUBMITTED | DATE APPROVED | NOTES
1 | Undertake planning activities | Customized scope of work | Delayed | 2017-04-21
2 | Conduct inception visit | Inception visit report | Complete
3 | Develop plan for obtaining ethical review from federalwide-certified and in-country IRB | Plan for obtaining ethical review from federalwide-certified and in-country IRB
4 | Prepare the study protocol and accompanying implementation plan | Survey protocol | In Progress
5 | Develop and issue RFP (if required) | Scope of work (with detailed fieldwork implementation plan, including team structure, fieldwork timeline, and logistics), RFP
6 | Prepare the sampling design | Sampling design plan | Not Started
7 | Coordinate with national statistical office to select PSUs | List of selected clusters (first stage sampling)
8 | Undertake country-specific customization of the core questionnaire (paper version) | Customized questionnaire (paper version)
9 | Translate questionnaire (paper version) | Translated questionnaire (paper version)
10 | Submit application for review to the IRB | Package of all IRB submission requirements for both international and in-country (if required)
11 | Establish range values for purposes of implementing range checks | File of range values (indicating which questionnaire items will have range checks and what the ranges will be)
12 | Subcontract to local partner organization | Contract signed with local survey organization
13 | Customize core questionnaire pretest protocol (including cognitive probes) | Questionnaire pretest protocol (including cognitive probes)
14 | Implement questionnaire pretest | Questionnaire pretest report
15 | Procure supplies and equipment (tablets and personal protective equipment) | Supply ordering plan and timeline (including customs management plan if supplies are being shipped to country)
16 | Develop CAPI pretest and pilot protocols | CAPI pretest and pilot protocols
17 | Develop and code programming specifications (CAPI only) | Programming specification tables
18 | Program questionnaire (either for CAPI data collection or for PAPI data entry) | CAPI data collection program or PAPI data entry program
19 | Prepare survey manuals:
| 19a - Interviewer Manual | Customized Interviewer Manual
| 19b - Supervisor Manual | Customized Supervisor Manual
| 19c - Organization Manual | Customized Survey Organization Manual
| 19d - Quality Control and Support Team Manual | Customized Quality Control and Support Team Manual
| 19e - Listing Manual | Customized Listing Manual
20 | Develop field check tables | Field check table shells
21 | Develop data monitoring plan | Data monitoring plan
22 | Prepare data cleaning plan | Data cleaning plan
23 | Develop fieldwork management and monitoring plan | Detailed fieldwork management and monitoring plan that includes regular progress reports throughout fieldwork
24 | Develop interviewer training plans and supporting materials
| 24a - Training plan | Interviewer training plan
| 24b - Agenda (facilitator and trainee versions) | Training agenda (facilitator and trainee versions)
| 24c - Attendance sheets | Customized attendance sheets
| 24d - Quizzes | Quizzes
| 24e - Role play exercises | Role play exercises
| 24f - Demonstration of field check tables and interpretation | Demonstration of field check tables and interpretation
| 24g - Demonstration of real-time remote fieldwork monitoring (if planned) | Demonstration of real-time remote fieldwork monitoring
| 24h - CAPI training materials (if relevant) | CAPI training materials
| 24i - Interviewer's training materials (slides, specific forms) | Interviewer training materials (including customized slides and forms)
| 24i - Supervisor training materials (incl. assignment and control sheets) | Supervisor training materials (including assignment and control sheets)
| 24j - IT staff training plan and materials (if relevant) | IT staff training plan and materials
25 | Implement listing operation | Listing field report and household listing
26 | Clean listing data and select households (on a rolling basis) | List of households selected for interview
27 | Ensure that IRB approval has been received | Approval from Federalwide-certified IRB and local IRB
28 | Implement training of trainers | Completion of training of trainers
29 | Implement CAPI pretest (as part of training of trainers) | Training of trainers and CAPI pretest report
30 | Implement interviewer training | Completion of interviewer training
31 | Implement pilot (as part of interviewer training) | Interviewer training and pilot report
32 | Implement data entry/data management pilot (as part of all-systems fieldwork pilot) | Data entry/data management pilot report
33 | Prepare data weighting protocol | Data weighting protocol
34 | Implement fieldwork | Weekly fieldwork report, plus summary fieldwork report at end of data collection activities
35 | Generate field check tables | Weekly field check tables
36 | Prepare data structure and codebook | Structure of the data files and expected format of the codebook
37 | Clean the data | Memo advising of data cleaning steps implemented according to plan, and notable findings during the cleaning process
38 | Weight the data | Memo advising that the weighting of the data has been completed according to protocol
39 | Prepare data quality assessment memo | Memo to include response rates, final set of field check tables and interpretation of key findings, and any other pertinent information regarding data quality
40 | Analyze the data | Produce frequencies, cross-tabulations, and any additional required statistical analyses
41 | Prepare final report tables | Final report tables (draft, final)
42 | Draft final report | Final report text (draft, final)
43 | Prepare protocol for rendering data suitable for public use | Protocol for preparation of public access data
44 | Prepare non-public access data files (maintains some PII, e.g., GPS coordinates) | Non-public access data files and supporting materials
45 | Prepare restricted access data files | Restricted access data files and supporting materials
46 | Prepare public access data files (excludes PII) | Public access data files and supporting materials
47 | Enter values in USAID'S Development Information Solution | Indicator estimates entered in USAID's Development Information Solution
Notes: IRB – institutional review board; RFP – request for proposal; PSU – primary sampling unit; CAPI – computer-assisted personal interviewing; CSPro – census and survey processing system; IT – information technology; PII – personally identifiable information
Note on A6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added ZOI Midline
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Should we denote that some are deliverables to the client and some are internal deliverables? Perhaps with an asterisk as in other documents?
Note on C10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updated deliverable to be a plan. The package is now deliverable for #10.
Note on C17: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updated from "Ethical clearance obtained" which is the deliverable for #27. Also though, which IRB is #10 referring to? In-country or federalwide or both - it's not clear. Reply: Both
Note on C20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New item in gantt chart
Note on C25: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updated from "Questionnaire programming plan" Should "PAPI data entry program" be included if we don't have PAPI references or guidance elsewhere?
Note on C28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updated from "Customized Supervisor Manual (CAPI) or Supervisor and Field Editor Manual (for PAPI Surveys)" to match Gannt chart
Note on C31: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Removed "and List Preparation Protocol" - do not reference this protocol anywhere else.
Note on C35: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Updated "with regular..." to be "that includes regular..."
Note on C44: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed "Tablet" to "CAPI"
Note on C45: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added - new item in Gantt chart
Note on C46: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Removed "and field editor"
Note on C51: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added "of trainers"
Note on C52: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Spelled out TOT and added "CAPI"
Note on C53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Added "interviewer"
Note on C54: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed "Main" to "Interviewer"
Note on C59: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: With the template codebook, "Expected format of the codebook" already exists. The codebook is not finalized until after data analysis is completed though, so the codebook itself isn't a deliverable here. Can the codebook pieces of this activity be removed from this line? They actually fit in as "supporting materials" in lines 44-46 for the final datasets?
Note on C67: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed "use" to "access" and added "and supporting materials"
Note on C68: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New item
Note on C69: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Changed "use" to "access" and added "and supporting materials"
Note on C70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: New item in Gantt chart

## Gantt Chart
Feed the Future Zone of Influence Midline Survey Tasks and Timeline |  | MONTH
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
1 | Undertake planning activities
2 | Conduct inception visit
3 | Develop plan for obtaining ethical review from federalwide-certified and in-country IRB
4 | Prepare the study protocol and accompanying implementation plan
5 | Develop and issue RFP (if required)
6 | Prepare the sampling design
7 | Coordinate with national statistical office to select PSUs
8 | Undertake country-specific customization of the core questionnaire (paper version)
9 | Translate questionnaire (paper version)
10 | Submit application for review to the IRB
11 | Establish range values for purposes of implementing range checks
12 | Subcontract to local partner organization
13 | Customize core questionnaire pretest protocol (including cognitive probes)
14 | Implement questionnaire pretest
15 | Procure supplies and equipment (tablets and personal protective equipment)
16 | Develop CSPro CAPI pretest and pilot protocols
17 | Develop and code programming specifications for CSPro CAPI
18 | Program questionnaire for CSPro CAPI data collection
19 | Prepare survey manuals:
19a - Interviewer Manual
19b - Supervisor Manual
19c - Organization Manual
19d - Quality Control and Support Team Manual
19e - Listing Manual
20 | Develop field check tables
21 | Develop data monitoring plan
22 | Prepare data cleaning plan
Feed the Future Zone of Influence Midline Survey Tasks and Timeline |  | MONTH 1: MONTH
|  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20
23 | Develop fieldwork management and monitoring plan
24 | Develop interviewer training plans and supporting materials
24a - Training plan
24b - Agenda (facilitator and trainee versions)
24c - Attendance sheets
24d - Quizzes
24e - Role play exercises
24f - Demonstration of field check tables and interpretation
24g - Demonstration of real-time remote fieldwork monitoring (if planned)
24h - CSPro CAPI training materials
24i - Interviewer's training materials (slides, specific forms)
24i - Supervisor training materials (incl. assignment and control sheets)
24j - IT staff training plan and materials (if relevant)
25 | Implement listing operation
26 | Clean listing data and select households (on a rolling basis)
27 | Ensure that IRB approval has been received
28 | Implement training of trainers
29 | Implement CSPro CAPI pretest (as part of training of trainers)
30 | Implement interviewer training
31 | Implement pilot (as part of interviewer training)
32 | Implement data entry/data management pilot (as part of all-systems fieldwork pilot)
33 | Prepare data weighting protocol
34 | Implement fieldwork
35 | Generate field check tables
36 | Prepare data structure and codebook
37 | Clean the data
38 | Weight the data
39 | Prepare data quality assessment memo
40 | Analyze the data
41 | Prepare final report tables
42 | Draft final report
43 | Prepare protocol for rendering data suitable for public use
44 | Prepare non-public access data files (maintains some PII, e.g., GPS coordinates)
45 | Prepare restricted access data files
46 | Prepare public access data files (excludes PII)
47 | Enter values in USAID'S Development Information Solution
Notes: IRB – institutional review board; RFP – request for proposal; PSU – primary sampling unit; CAPI – computer-assisted personal interviewing; CSPro – census and survey processing system; PII – personally identifiable information
This Gantt chart is predicated on the use of existing core survey documentation (questionnaire, manuals, data entry program, etc.) that need only be customized for country-specific details. Addition of new questions, modules, or procedures will require considered revision and extension of the timeline represented here.

## ref
StatusCats
Not Started | Not Started
In Progress | In Progress
Delayed | Delayed
Complete | Complete