## About the Survey Tracker
FEED THE FUTURE SURVEY IMPLEMENTATION DOCUMENT
Survey Implementation Tracker [YEAR] [COUNTRY] Phase Two Zone of Influence Midline Indicator Assessment
ABOUT THE SURVEY IMPLEMENTATION TRACKER:
The Survey Implementation Tracker consists of a list of tasks and deliverables designed to help USAID Country Managers and Contractor Country Leads systematically monitor and manage the implementation of phase two Zone of Influence midline indicator assessments conducted for Feed the Future. This Tracker serves as: - a map of the critical aspects of the survey processes that need to be in place to achieve minimum methodological standards; - a planning guide to support alignment of survey processes, staff, and resources; - a framework into which other guidance documents fit, including the survey protocol, questionnaires, and survey manuals; - a monitoring tool that helps managers to track overall survey progress and deliverables to ensure none are skipped or forgotten.
HOW TO USE THE SURVEY TRACKER
Item | Description
Tasks: | All requisite tasks for the survey to be performed by the Contractor are pre-filled in the Tracker. Managers may adapt the Tracker by adding other specific tasks that they deem important.
Deliverable: | All key deliverables for each task are pre-filled in the Tracker. Managers may wish to add more, depending on the extent to which close management may be required.
Status: | There are four status categories - Not Started, In Progress, Delayed, and Complete. For each task, indicate where it is in the process.
Dates: | All due dates for each deliverable should be discussed and agreed on before they are entered into the Tracker. Timelines vary for each deliverable, and the Survey Manager should use the Gantt Chart as a guide for estimating the dates. One to two weeks should be allowed for review of submitted deliverables. One to two weeks should also be allowed for editing and formatting of deliverables.

## Survey Tracker Management Tool
Key: Survey Status Categories
|  |  | Not Started | In Progress | Delayed | Complete | Pending Approval | Approved
|  |  | OFF | OFF | OFF | OFF | OFF | OFF
|  |  |  | CONTRACTOR SUBMISSION |  | USAID REVIEW |  | CONTRACTOR REVISION, EDITING, AND FORMATTING |  | SUBMITTED | APPROVED
Feed the Future P2-ZOI Midline Indicator Assessment Implementation Tracker
| TASK | DELIVERIABLES | STATUS | START DATE | END DATE | START DATE2 | END DATE2 | DATE COMPLETED | DATE APPROVED | DATE SUBMITTED | DATE APPROVED2 | NOTES
1 | Undertake planning activities | Customized work plan with Gantt chart and list of deliverables* | Not Started
2 | Conduct inception visit or virtual consultation | Inception visit or virtual consultation report | Not Started
3 | Develop plan for obtaining ethical review from federal wide-certified and in-country IRB | Plan to obtain approval for midline indicator assessment from a federal wide-certified IRB and an ethics committee the survey country | Not Started
4 | Prepare the survey protocol | Survey protocol* | Not Started
5 | Develop a scope of work for the local survey implementation partner and issue a request for proposals (if applicable) | Request for proposals with scope of work that details fieldwork implementation plan, including team structure, fieldwork timeline, and logistics | Not Started
6 | Prepare the sampling design document | Sampling design document | Not Started
7 | Coordinate with the national statistics office to select primary sampling units | List of selected clusters (first-stage sampling) | Not Started
8 | Select local survey implementation partner and submit the subcontracting package to the USAID Contracting Officer for approval (if applicable) | Subcontracting package for USAID approval* (if applicable) | Not Started
9 | Issue subcontract to local survey implementation partner | Fully executed subcontract with local survey implementation partner | Not Started
10 | Procure supplies and equipment (tablets and personal protective equipment) | Supply ordering plan and timeline (including customs management plan if supplies are being shipped to country) | Not Started
11 | Customize the core main and parallel survey paper questionnaires as per country SOW | Customized main and parallel survey paper questionnaires* | Not Started
12 | Conduct initial capacity assessment of the in-country local survey implementation partner and develop a capacity strengthening plan | Capacity strengthening plan* | Not Started
13 | Translate customized main and parallel survey paper questionnaires according to established translation protocol | Translated customized main and parallel survey paper questionnaires | Not Started
14 | Submit application for review to the federal wide-certified IRB and in-country ethics committee | Submission packages for review by a federal wide-certified IRB and an ethics committee in the survey country | Not Started
15 | Develop cognitive probes for the paper questionnaire pretest | Cognitive probes for paper questionnaire pretest | Not Started
16 | Implement paper questionnaire pretest according to established protocol | Paper questionnaire pretest report* | Not Started
17 | Customize the core main and parallel survey CSPro CAPI data collection applications | Customized CSPro applications for main and parallel surveys | Not Started
18 | Prepare survey manuals: |  | Not Started
| a—Interviewer’s Manual | Customized Interviewer’s Manual* | Not Started
| b—Field Supervisor’s Manual | Customized Field Supervisor’s Manual | Not Started
| c—Quality Control and Support Team Manual | Customized Quality Control and Support Team Manual | Not Started
| d—In-Country Data Manager’s Manual | Customized In-Country Data Manager’s Manual | Not Started
19 | Prepare fieldwork management plan, including the field movement plan, field check tables, data quality control plan | Fieldwork management, including field movement plan, field check tables, and data quality control plan | Not Started
20 | Develop plans to train survey staff | Training plans, including customized training agendas (facilitator and trainee versions) for all trainings (training of trainers, Interviewers’, Field Supervisors’, QCS Teams’, and ICDM’s) | Not Started
21 | Develop training materials for all survey staff trainings: | Customized attendance sheets, quizzes, role play exercises, slides, and forms | Not Started
| a—Interviewers’ training |  | Not Started
| b—Field Supervisors’ training |  | Not Started
| c—QCS Teams’ training |  | Not Started
| d—ICDM’s training |  | Not Started
22 | Implement household listing operation according to the CAPI Household Listing Manual | Household listing operation report* and household listings | Not Started
23 | Prepare listing data and select households (on a rolling basis) | List of households selected for interview | Not Started
24 | Ensure that IRB approvals have been received | Documentation of approval from federal wide-certified IRB and in-country IRB, as applicable | Not Started
25 | Implement training of trainers and CSPro CAPI pretest according to the CAPI pretest protocol | Training of trainers and CAPI pretest report* | Not Started
26 | Implement Interviewers’ training and pilot according to the pilot protocol | Interviewers’ training and pilot report* | Not Started
27 | Implement fieldwork | Weekly fieldwork report, plus summary fieldwork report at end of data collection activities | Not Started
28 | Generate field check tables | Weekly field check tables (included in weekly fieldwork report) | Not Started
29 | Prepare data weighting protocol | Data weighting protocol | Not Started
30 | Process data in CSPro according to Feed the Future’s standard data processing and finalization procedures | Cleaned CSPro dataset | Not Started
31 | Calculate sample weights and add to the data | Cleaned CSPro dataset with sample weights added | Not Started
32 | Prepare the data quality assessment memo | Data quality assessment memo presenting response rates, final set of field check tables, key findings from data cleaning and data weighting tasks, and any other pertinent information regarding data quality | Not Started
33 | Analyze the data and prepare midline indicator assessment results tables | Final midline indicator assessment results tables | Not Started
34 | Draft midline indicator assessment report, including rounds of review and revision | Final midline indicator assessment report* | Not Started
35 | Prepare and conduct survey results dissemination presentation | Final results dissemination presentation slides | Not Started
36 | Develop communication products as per the agreed scope of work | Communication products* | Not Started | [9 empty] | .
37 | Prepare non-public, restricted, public access datasets, including supporting materials | Non-public access, restricted, and public access datasets and supporting materials | Not Started
38 | Enter values in USAID’s Development Information Solution | P2-ZOI Midline Survey indicator values entered in USAID’s Development Information Solution | Not Started
39 | Upload final midline indicator assessment report to the Development Experience Clearinghouse after USAID receives approval by the host country government | Final midline indicator assessment report uploaded to the Development Experience Clearinghouse | Not Started
40 | Conduct final capacity strengthening assessment and write final capacity strengthening report (if applicable) | Final capacity strengthening report* | Not Started
41 | Upload final, COR-approved communications products to the Development Experience Clearinghouse | Final communications products uploaded to the Development Experience Clearinghouse | Not Started
Capacity strengthening activities
CS1 | Placeholder for local survey implementation partner capacity strengthening activities X] | Capacity strengthening report | Not Started
CS2 | Placeholder for capacity strengthening activities [X] for other stakeholders (as applicable) | Capacity strengthening report | Not Started
Note: Deliverables denoted with one asterisk (*) and bold font require COR approval. Deliverables denoted with only bold font (no asterisks) must be submitted to USAID but do not require COR approval. Deliverables denoted in regular font (no asterisks or bold font) do not have to be submitted to USAID but should be produced by the Contractor.

## P2-ZOI midline Gantt chart
Feed the Future P2-ZOI midline |  | MONTH
indicator assessment tasks and timeline |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23
1 | Undertake planning activities (prepare workplan with Gantt chart and list of deliverables) | bar: MONTH 1
2 | Conduct inception visit or virtual consultation | bar: MONTH 1
3 | Develop plan for obtaining ethical review from federal wide-certified and in-country IRB | bar: MONTH 1
4 | Prepare the survey protocol | bar: MONTH 1 to MONTH 3
5 | Develop a scope of work for the local survey implementation partner and issue a request for proposals (if applicable) | bar: MONTH 1 to MONTH 2
6 | Prepare the sampling design document | bar: MONTH 2 to MONTH 4
7 | Coordinate with the national statistics office to select primary sampling units | bar: MONTH 2 to MONTH 3
8 | Select local survey implementation partner and submit the subcontracting package to the USAID Contracting Officer for approval (if applicable) | bar: MONTH 2 to MONTH 3
9 | Issue subcontract to local survey implementation partner | bar: MONTH 2 to MONTH 3
10 | Procure supplies and equipment (tablets and personal protective equipment) | bar: MONTH 2 to MONTH 4
11 | Customize the core main and parallel survey paper questionnaires as per country SOW | bar: MONTH 2 to MONTH 4
12 | Conduct initial capacity assessment of the in-country local survey implementation partner and develop a capacity strengthening plan | bar: MONTH 3 to MONTH 4
13 | Translate customized main and parallel survey paper questionnaires according to established translation protocol | bar: MONTH 3 to MONTH 4
14 | Submit application for review to the federal wide-certified IRB and in-country ethics committee | bar: MONTH 3 to MONTH 4
15 | Develop cognitive probes for the paper questionnaire pretest | bar: MONTH 4
16 | Implement paper questionnaire pretest according to established protocol | bar: MONTH 5
17 | Customize the core main and parallel survey CSPro CAPI data collection applications | bar: MONTH 4 to MONTH 6
18 | Prepare survey manuals: | bar: MONTH 4 to MONTH 6
a—Interviewer’s Manual | bar: MONTH 4 to MONTH 6
b—Field Supervisor’s Manual | bar: MONTH 4 to MONTH 6
c—Quality Control and Support Team Manual | bar: MONTH 4 to MONTH 6
d—In-Country Data Manager’s Manual | bar: MONTH 4 to MONTH 6
19 | Prepare fieldwork management plan, including the field movement plan, field check tables, data quality control plan | bar: MONTH 4 to MONTH 7
20 | Develop plans to train survey staff | bar: MONTH 4 to MONTH 7
21 | Develop training materials for all survey staff trainings: | bar: MONTH 4 to MONTH 7
a—Interviewers’ training | bar: MONTH 4 to MONTH 7
b—Field Supervisors’ training | bar: MONTH 4 to MONTH 7
c—QCS Teams’ training | bar: MONTH 4 to MONTH 7
d—ICDM’s training | bar: MONTH 4 to MONTH 7
22 | Implement household listing operation according to the CAPI Household Listing Manual | bar: MONTH 6 to MONTH 7
23 | Prepare listing data and select households (on a rolling basis) | bar: MONTH 6 to MONTH 7
24 | Ensure that IRB approvals have been received | bar: MONTH 7
25 | Implement training of trainers and CSPro CAPI pretest according to the CAPI pretest protocol | bar: MONTH 7 to MONTH 8
26 | Implement Interviewers’ training and pilot according to the pilot protocol | bar: MONTH 8
27 | Implement fieldwork | bar: MONTH 9 to MONTH 12
28 | Generate field check tables | bar: MONTH 9 to MONTH 13
29 | Prepare data weighting protocol | bar: MONTH 9 to MONTH 12
30 | Process data in CSPro according to Feed the Future’s standard data processing and finalization procedures | bar: MONTH 13 to MONTH 15
31 | Calculate sample weights and add to the data | bar: MONTH 13 to MONTH 14
32 | Prepare the data quality assessment memo | bar: MONTH 15
33 | Analyze the data and prepare midline indicator assessment results tables | bar: MONTH 15 to MONTH 20
34 | Draft midline indicator assessment report, including three rounds of review and revision | bar: MONTH 17 to MONTH 20
35 | Prepare and conduct survey results dissemination presentation | bar: MONTH 17 to MONTH 21
36 | Develop communication products as per the agreed scope of work | bar: MONTH 17 to MONTH 23
37 | Prepare non-public, restricted, public access datasets, including supporting materials | bar: MONTH 17 to MONTH 20
38 | Enter values in USAID’s Development Information Solution | bar: MONTH 20
39 | Upload final midline indicator assessment report to the Development Experience Clearinghouse after USAID receives approval by the host country government | bar: MONTH 20 to MONTH 23
40 | Conduct final capacity strengthening assessment and write final capacity strengthening report (if applicable) | bar: MONTH 21 to MONTH 23
41 | Upload final, COR-approved communications products to the Development Experience Clearinghouse | bar: MONTH 21 to MONTH 23
Capacity Strengthening
CS1 | Placeholder for local survey implementation partner capacity strengthening activities X] | bar: MONTH 7 to MONTH 23
CS2 | Placeholder for capacity strengthening activities [X] for other stakeholders (as applicable) | bar: MONTH 5 to MONTH 23